# Phased Implementation Plan & Roadmap

Revision: 1 Last modified: 2026-07-24T00:00:00Z

## Phase 1: Foundation (Weeks 1–4)

Goal: Establish the LLM infrastructure, Constitution integration, MCP deployment, and SpecKit installation so all subsequent phases build on a solid foundation.

### Week 1 — Environment & LLM Setup

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Mon | Provision Helix LLM API access — obtain API key, endpoint, rate limits | Ops | API credentials in .env |
| Mon | Install node >=18, bash >=5, jq, ripgrep, graphviz on all hosts | Ops | Verified command -v for each tool |
| Tue | Clone helix-nano-bridge template repo, scaffold directory structure | Dev | tree constitution/submodules/helix-nano-bridge/ |
| Tue | Create constitution/submodules/helix-nano-bridge/helix-deps.yaml per §11.4.28(C) | Dev | Valid YAML, parsed by constitution/scripts/check_deps.sh |
| Wed | Configure Helix LLM fallback chain: helix-nano → deepseek-v4-pro → opus-xhigh | Dev | .env.template with all 3 endpoints |
| Wed | Write bin/llm_probe.sh — health-check script that tests all 3 LLM backends | Dev | Exit 0 = all backends reachable |
| Thu | Write lib/llm_client.sh — unified client calling Helix API with retry + backoff | Dev | Unit test: 3 consecutive successful calls |
| Fri | Integration test: llm_probe.sh → all backends GREEN, fallback chain verified | QA | Test log in qa-results/week1/ |
| Fri | Week 1 retrospective + docs/CONTINUATION.md update | All | Updated §3 Active work |

### Week 2 — Constitution Integration

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Mon | Study constitution/Constitution.md §11.4.27 (HelixQA), §11.4.43 (TDD), §11.4.115 (RED/GREEN) | Dev | Notes in docs/research/constitution_audit.md |
| Tue | Map every SpecKit extension hook to the corresponding Constitution §-letter | Dev | Traceability matrix docs/research/speckit_constitution_map.md |
| Tue | Write CM-HELIX-NANO-BRIDGE-EXTENSION-EXISTS pre-build gate | Dev | Gate in pre_build_verification.sh |
| Wed | Write paired §1.1 meta-test mutation for the gate | Dev | Mutation in meta_test_false_positive_proof.sh |
| Thu | Wire helix-nano-bridge into docs_chain per §11.4.106 | Dev | .docs_chain/contexts/helix_nano_bridge.yaml |
| Fri | Verify all 5 Constitution CM-COVENANT-* propagation gates still GREEN after extension | QA | pre_build_verification.sh exit 0, 0 WARN |
| Fri | Week 2 retrospective | All | CONTINUATION.md updated |

### Week 3 — MCP Server Deployment

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Mon | Scaffold superbridge-mcp TypeScript project: package.json, tsconfig.json, src/index.ts | Dev | npm install && npm run build succeeds |
| Tue | Implement execute_tdd_cycle tool with RED→GREEN→VERIFY pipeline | Dev | Integration test: mocked TDD cycle exits correctly |
| Wed | Implement verify_anti_bluff tool — evidence file parsing + pattern matching | Dev | Unit tests for golden-good / golden-bad inputs |
| Thu | Implement nano_task_decompose + nano_task_execute + nano_task_graph tools | Dev | 5 tools registered, each with input validation |
| Fri | Wire MCP server into Claude Code, Codex, Cursor, Gemini CLI configs | Dev | mcp_server_test.sh probes each agent |
| Fri | Week 3 retrospective | All | CONTINUATION.md updated |

### Week 4 — SpecKit Installation & Smoke Test

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Mon | Install SpecKit CLI: specify --version resolves | Dev | specify --version ≥ 2.0.0 |
| Tue | Install SpecKit extensions: superb, helix-nano-bridge (skeleton) | Dev | specify extension list shows both |
| Tue | Create skeleton extension.yml with all 5 commands registered | Dev | specify helix-nano-bridge --help prints usage |
| Wed | Write speckit.helix-nano-bridge.decompose.md command spec | Dev | Markdown file with full spec per EXTENSION_DEVELOPMENT.md |
| Thu | Write remaining 4 command specs: execute.md, graph.md, status.md, retry.md | Dev | All 5 command specs complete |
| Fri | End-to-end smoke test: specify feature new test-feature → decompose → execute (dry-run) | QA | qa-results/week4/smoke_test.log |
| Fri | Phase 1 milestone review — foundation DECLARED READY | All | CM-HELIX-NANO-BRIDGE-EXTENSION-EXISTS GREEN |

### Phase 1 Deliverables

constitution/submodules/helix-nano-bridge/
├── bin/
│   ├── llm_probe.sh                    # LLM health check
│   └── helix-nano-bridge               # Main entry point (skeleton)
├── lib/
│   └── llm_client.sh                   # Unified LLM client
├── spec/
│   └── helix-nano-bridge/
│       ├── extension.yml               # SpecKit extension manifest
│       ├── speckit.helix-nano-bridge.decompose.md
│       ├── speckit.helix-nano-bridge.execute.md
│       ├── speckit.helix-nano-bridge.graph.md
│       ├── speckit.helix-nano-bridge.status.md
│       └── speckit.helix-nano-bridge.retry.md
├── mcp/
│   └── superbridge-mcp/
│       ├── package.json
│       ├── tsconfig.json
│       ├── src/index.ts                # 5-tool MCP server
│       └── dist/index.js               # Built artifact
├── helix-deps.yaml                     # §11.4.28(C) dependency spec
└── .env.template

## Phase 2: Nano-Task Engine (Weeks 5–8)

Goal: Build the nano-task decomposition engine, DAG dependency resolver, TDD execution pipeline, and anti-bluff oracle — the core intellectual property.

### Week 5 — Nano-Task Schema & Decompose Command

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Mon | Define nano-tasks.json JSON Schema (JSON Schema draft-2020-12) | Dev | spec/nano-tasks.schema.json — validates with ajv |
| Tue | Implement nano_decompose_task() in lib/nano_bridge_common.sh | Dev | Parses tasks.md → extracts files/symbols |
| Wed | Implement nano_build_dependency_dag() — adjacency list from plan.md | Dev | DAG builder with test coverage |
| Thu | Implement nano_detect_cycles() — Kahn's algorithm with DFS fallback | Dev | Cycle detection test: inject cycle → detected |
| Fri | Wire helix-nano-bridge decompose command end-to-end | Dev | nano-tasks.json produced from real tasks.md |
| Fri | Week 5 retrospective | All | CONTINUATION.md updated |

### Week 6 — DAG Engine & Phase Assignment

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Mon | Implement nano_assign_phases() — level-order grouping | Dev | Tasks assigned to phases, no file collisions in same phase |
| Tue | Implement critical path computation — longest path in DAG | Dev | nano-tasks.json includes critical_path_length |
| Wed | Implement nano_generate_mermaid() / nano_generate_dot() | Dev | Mermaid and DOT output renderable in tools |
| Thu | Wire helix-nano-bridge graph command | Dev | --format mermaid → valid chart, --format svg → renders |
| Fri | Test DAG correctness on 10 sample tasks.md files (varying complexity) | QA | All 10 produce acyclic, correctly-phased DAGs |
| Fri | Week 6 retrospective | All | CONTINUATION.md updated |

### Week 7 — TDD Execution Engine

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Mon | Implement nano_execute_single_task() — RED→GREEN→VERIFY cycle | Dev | Core execution loop |
| Tue | Implement RED phase: run test, assert FAIL, capture evidence | Dev | RED_<timestamp>.log with exit code ≠ 0 |
| Wed | Implement GREEN phase: run test, assert PASS, 3-iteration consistency | Dev | GREEN_<timestamp>.log with exit code = 0, all 3 identical |
| Thu | Implement VERIFY phase: anti-bluff oracle checks evidence files | Dev | verdict.json with PASS/FAIL + rationale |
| Fri | Wire helix-nano-bridge execute command — phase-by-phase execution | Dev | Phases execute in order, parallel within phase |
| Fri | Week 7 retrospective | All | CONTINUATION.md updated |

### Week 8 — Unit Tests & Anti-Bluff Oracle

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Mon | Write unit tests for nano_decompose_task() — 10+ test cases | Dev | 100% pass rate |
| Tue | Write unit tests for nano_build_dependency_dag() — cycle/no-cycle/multi-dep | Dev | 100% pass rate |
| Wed | Write unit tests for nano_execute_single_task() — RED-fail/GREEN-pass/verify | Dev | 100% pass rate |
| Thu | Implement anti-bluff oracle golden-good / golden-bad fixtures | Dev | Golden-good PASSES oracle, golden-bad FAILS it |
| Fri | Wire paired §1.1 mutation for the execution gate | Dev | Stripping gate check → gate FAILs |
| Fri | Phase 2 milestone review — nano-task engine DECLARED READY | All | CM-NANO-TASK-ENGINE GREEN |

### Phase 2 Deliverables

lib/
├── nano_bridge_common.sh               # Full implementation (~600 lines)
├── anti_bluff_oracle.sh                # Evidence validation oracle
├── test_nano_bridge.sh                 # Unit test suite for library
└── test_anti_bluff_oracle.sh           # Oracle golden-good/golden-bad tests

bin/
├── helix-nano-bridge-decompose         # Full implementation
├── helix-nano-bridge-execute           # Full implementation
├── helix-nano-bridge-graph             # Full implementation
├── helix-nano-bridge-status            # Full implementation
└── helix-nano-bridge-retry             # Full implementation

spec/
└── nano-tasks.schema.json              # JSON Schema for nano-tasks.json

qa-results/week8/
├── unit_tests.log                      # All unit tests GREEN
├── decompose_10_samples.log            # 10/10 DAGs correct
└── oracle_golden_fixtures.log          # Good=PASS, Bad=FAIL

## Phase 3: Superbridge Integration (Weeks 9–12)

Goal: Build the MCP server, SuperB extension integration, and E2E tests so the full pipeline works from tasks.md to verified implementation.

### Week 9 — MCP Server Completion

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Mon | Complete execute_tdd_cycle tool — full RED→GREEN→VERIFY with evidence capture | Dev | Tool returns structured PASS/FAIL verdict |
| Tue | Complete verify_anti_bluff tool — expected/forbidden pattern matching | Dev | Tool catches golden-bad inputs |
| Wed | Complete nano_task_decompose tool — calls bash library via exec | Dev | Tool produces valid nano-tasks.json |
| Thu | Complete nano_task_execute + nano_task_graph tools | Dev | All 5 tools functional |
| Fri | MCP server integration test: Claude Code calls execute_tdd_cycle on a mock task | QA | PASS verdict with evidence JSON |
| Fri | Week 9 retrospective | All | CONTINUATION.md updated |

### Week 10 — SuperB Integration

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Mon | Map superb 7-command workflow to helix-nano-bridge 5 commands | Dev | superb/integrations/helix-nano-bridge.yaml |
| Tue | Wire superb:plan → decompose, superb:implement → execute | Dev | SpecKit hooks fire correctly |
| Wed | Implement implementation-gate.js — 7 checks before execution | Dev | node implementation-gate.js <feature_dir> |
| Thu | Wire superb:verify → status --format report --evidence | Dev | SuperB verify phase shows nano-task status |
| Fri | Wire superb:ship gated on 100% GREEN nano-tasks | Dev | Ship blocked when any task FAIL |
| Fri | Week 10 retrospective | All | CONTINUATION.md updated |

### Week 11 — E2E Tests

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Mon | Create test feature: specify feature new e2e-nano-test with 3 tasks | Dev | tasks.md with 3 tasks, 5 dependencies |
| Tue | Run full pipeline: tasks.md → decompose → execute → graph → status | QA | 100% GREEN, evidence captured for all nano-tasks |
| Wed | Inject a bug: modify a RED test to pass when it should fail → verify gate BLOCKS | QA | Gate exit 2, FAIL verdict recorded |
| Thu | Test retry: force-fail 2 tasks → retry → tasks recover and go GREEN | QA | Retry log shows RED→GREEN→VERIFY cycles |
| Fri | Test parallel execution: 24 independent nano-tasks → all run concurrently within phase | QA | Phase execution time ≤ sum of longest 2 tasks |
| Fri | Week 11 retrospective | All | CONTINUATION.md updated |

### Week 12 — Completion & Polish

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Mon | Write user documentation: docs/guides/HELIX_NANO_BRIDGE_USER_GUIDE.md | Dev | Complete user guide, exported to HTML+PDF+DOCX |
| Tue | Write installation guide: docs/guides/HELIX_NANO_BRIDGE_INSTALL.md | Dev | Step-by-step install, verified on fresh clone |
| Wed | Polish error messages — every exit code has a human-readable explanation | Dev | helix-nano-bridge --help shows all exit codes |
| Thu | Add helix-nano-bridge to constitution/scripts/post_update_hook.sh per §11.4.164 | Dev | Auto-registered on constitution pull |
| Fri | Phase 3 milestone review — Superbridge integration DECLARED READY | All | Full E2E test log GREEN |
| Fri | Week 12 retrospective | All | CONTINUATION.md updated |

### Phase 3 Deliverables

mcp/superbridge-mcp/
├── src/
│   ├── index.ts                        # 5-tool MCP server (complete)
│   ├── tdd_cycle.ts                    # execute_tdd_cycle implementation
│   ├── anti_bluff.ts                   # verify_anti_bluff implementation
│   ├── decompose.ts                    # nano_task_decompose implementation
│   ├── execute.ts                      # nano_task_execute implementation
│   └── graph.ts                        # nano_task_graph implementation
├── tests/
│   ├── tdd_cycle.test.ts
│   ├── anti_bluff.test.ts
│   ├── decompose.test.ts
│   └── e2e.test.ts
├── dist/                               # Built JS output
└── package.json

superb/integrations/
└── helix-nano-bridge.yaml              # SuperB 7-command wiring

bin/
└── implementation-gate.js              # Pre-execution gate (7 checks)

docs/guides/
├── HELIX_NANO_BRIDGE_USER_GUIDE.md
└── HELIX_NANO_BRIDGE_INSTALL.md

qa-results/week11/
├── e2e_full_pipeline.log               # GREEN
├── gate_blocks_bad_test.log            # Gate caught the injected bug
├── retry_recovery.log                  # Tasks recovered
└── parallel_benchmark.log              # Performance data

## Phase 4: Production Hardening (Weeks 13–16)

Goal: Multi-host deployment, 100% test coverage, performance benchmarking, security audit, and documentation finalization — ready for production use.

### Week 13 — Multi-Host RPC & Scalability

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Mon | Implement superbridge-mcp over HTTP/SSE transport (beyond stdio) | Dev | MCP server listens on TCP port, SSE streaming |
| Tue | Implement remote execution: nano-tasks dispatched to worker nodes | Dev | Task dispatched via POST /execute to remote MCP server |
| Wed | Implement distributed evidence store: shared qa-results/ over NFS/SSHFS | Dev | All hosts read/write same evidence directory |
| Thu | Implement leader election for phase coordination — only one host advances phases | Dev | Leader lock via flock on shared NFS |
| Fri | Load test: 4 worker nodes, 200 nano-tasks, measure throughput | QA | Throughput report in qa-results/week13/parallel_benchmark.md |
| Fri | Week 13 retrospective | All | CONTINUATION.md updated |

### Week 14 — 100% Test Coverage

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Mon | Audit current test coverage — identify gaps | QA | Coverage report: coverage_report.json |
| Tue | Write tests for all error paths in nano_bridge_common.sh | Dev | Every exit 1/2/3/4 path has a test |
| Wed | Write tests for all 5 MCP tools with edge cases | Dev | npm test → 100% pass, 80%+ coverage |
| Thu | Write chaos tests per §11.4.85: process death, disk full, OOM injection | Dev | Chaos tests in tests/chaos/ |
| Fri | Write stress tests per §11.4.85: 100 concurrent decomposes, 1000-task DAG | QA | Stress report in qa-results/week14/stress_tests.md |
| Fri | Week 14 retrospective | All | CONTINUATION.md updated |

### Week 15 — Performance Benchmarking & Security Audit

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Mon | Benchmark decompose: 50-task tasks.md → nano-tasks (target: <5s) | QA | Latency p50/p95/p99 in benchmark report |
| Tue | Benchmark execute: 50 nano-tasks sequential (target: <2 min) | QA | Per-task latency distribution |
| Wed | Benchmark graph: 500-node DAG → Mermaid/DOT/SVG (target: <1s) | QA | Format-specific rendering times |
| Thu | Security audit: MCP server input validation, injection vectors, credential handling | Sec | Audit report in docs/audit/helix_nano_bridge_security.md |
| Fri | Fix all HIGH/MEDIUM security findings | Dev | Re-audit: 0 HIGH, 0 MEDIUM findings |
| Fri | Week 15 retrospective | All | CONTINUATION.md updated |

### Week 16 — Documentation & Release

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Mon | Finalize EXTENSION_DEVELOPMENT.md — ensure every section complete | Dev | Document passes CM-DOC-REVISION-HEADER-PRESENT |
| Tue | Finalize IMPLEMENTATION_PLAN.md — verify all weeks mapped to actual deliverables | Dev | Document passes CM-DOC-REVISION-HEADER-PRESENT |
| Wed | Generate all 4 export formats (MD+HTML+PDF+DOCX) per §11.4.65 | Dev | All mtimes ≥ source .md |
| Thu | Run full Constitution compliance sweep — all CM-* gates GREEN | QA | pre_build_verification.sh exit 0, 0 FAIL, 0 WARN |
| Fri | Tag constitution Submodule + create release helix-nano-bridge-v1.0.0 | Ops | Tag on all remotes, pack.sh archive published |
| Fri | Phase 4 milestone review — PRODUCTION READY declared | All | All 4 phases complete |

### Phase 4 Deliverables

mcp/superbridge-mcp/
├── src/
│   └── transport/
│       ├── stdio.ts                    # Existing stdio transport
│       └── http_sse.ts                 # New HTTP/SSE transport
├── tests/
│   ├── chaos/
│   │   ├── process_death.test.ts
│   │   ├── disk_full.test.ts
│   │   └── oom_injection.test.ts
│   └── stress/
│       ├── concurrent_decompose.test.ts
│       └── large_dag.test.ts
└── coverage/                           # Istanbul coverage reports

docs/
├── audit/
│   └── helix_nano_bridge_security.md   # Security audit findings
├── benchmarks/
│   └── performance_2026Q3.md           # Latency + throughput data
└── changelogs/
    └── v1.0.0.md                       # Release changelog

dist/
└── helix-nano-bridge-1.0.0.tar.gz      # Packaged release

## Milestones & Deliverables

| Milestone | End of Phase | Deliverables | Evidence |
| --- | --- | --- | --- |
| M1: Foundation | Week 4 | LLM configured, SpecKit installed, MCP skeleton running, 5 command specs complete | llm_probe.sh GREEN, specify helix-nano-bridge --help works, MCP server connects to Claude Code |
| M2: Nano-Task Engine | Week 8 | Decompose, execute, graph, status, retry all functional; DAG engine correct; anti-bluff oracle validated | All 5 commands tested on real tasks.md, nano-tasks.json valid, golden-good/bad fixtures pass |
| M3: Superbridge Integration | Week 12 | MCP server complete (5 tools), SuperB integrated, E2E pipeline GREEN, user docs published | Full E2E log: decompose → execute → graph → status all GREEN |
| M4: Production Ready | Week 16 | Multi-host, 100% coverage, security audited, performance benchmarked, documented, tagged | pre_build_verification.sh 0 FAIL 0 WARN, release tag pushed, pack.sh archive with SHA256 |

## Risk Register

| # | Risk | Probability | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R1 | Helix LLM API rate-limits during decompose phase | Medium | High | Fallback to deepseek-v4-pro; cache decompositions; batch LLM requests | Dev Lead |
| R2 | Dependency cycles in complex tasks.md files | Medium | Medium | Kahn's algorithm + DFS fallback in nano_detect_cycles(); operator-override flag | Dev |
| R3 | MCP server stdio transport incompatible with some agents | Medium | High | Ship both stdio and HTTP/SSE transports; test on all 4 agents in Week 3 | Dev |
| R4 | Evidence directory fills disk during long execution runs | Low | High | Per-task evidence size budget; auto-prune on GREEN; disk-space gate before execution | Ops |
| R5 | Phase assignment creates false sharing (two tasks modify same file) | Medium | Medium | Phase collision detection in nano_assign_phases(); implementation-gate.js check #7 | Dev |
| R6 | Constitution amendment invalidates SpecKit hook mapping | Low | High | CM-HELIX-NANO-BRIDGE-EXTENSION-EXISTS gate catches drift; constitution/scripts/post_update_hook.sh auto-revalidates | Dev Lead |
| R7 | Threadripper NUMA topology causes uneven task distribution | Medium | Low | numactl --cpunodebind per-worker; hardware detection auto-configures | Dev |
| R8 | SpecKit API breaks backward compatibility (v3.x) | Low | Medium | Extension manifest declares specKitVersion: ">=2.0.0"; pin version in CI | Dev |
| R9 | Security vulnerability in MCP server input handling | Medium | Critical | Input validation on all 5 tools; security audit Phase 4 Week 15; never eval user input | Sec |
| R10 | Operator time unavailable for milestones (blocked decisions) | Medium | High | Per §11.4.66 interactive clarification; autonomous decisions on low-blast-radius items per §11.4.101 | PM |

## Resource Requirements

### Hardware (per development host)

| Component | Minimum | Recommended | Purpose |
| --- | --- | --- | --- |
| CPU | 16 cores | 32+ cores (Threadripper) | Parallel nano-task execution |
| RAM | 32 GB | 64 GB | LLM context windows + parallel workers |
| GPU | None | NVIDIA RTX 4090 / A6000 | LLM inference offload |
| Storage | 50 GB free | 200 GB NVMe | Evidence artifacts, build artifacts |
| Network | 1 Gbps | 10 Gbps | Multi-host coordination, evidence sync |

### Software

| Tool | Version | Purpose |
| --- | --- | --- |
| Node.js | ≥18 LTS | MCP server runtime |
| Bash | ≥5.0 | Core scripting |
| jq | ≥1.6 | JSON processing |
| ripgrep | ≥13 | Fast file search |
| Graphviz | ≥2.50 | DAG rendering (DOT/SVG/PNG) |
| TypeScript | ≥5.0 | MCP server source |
| SpecKit CLI | ≥2.0.0 | Extension host |
| Superpowers CLI | ≥3.1.0 | Skill host |

### Personnel

| Role | Count | Commitment |
| --- | --- | --- |
| Lead Developer | 1 | Full-time, 16 weeks |
| Developer (MCP + JS) | 1 | Full-time, weeks 3–15 |
| QA Engineer | 1 | 50%, weeks 4–16 |
| Security Auditor | 1 | 2 weeks, weeks 15 |
| Operator/PM | 1 | Advisory, milestone gates |

## Success Criteria (Anti-Bluff Evidence)

Each phase is complete ONLY when the following evidence is captured:

### Phase 1 Success Criteria

| # | Criterion | Evidence Type |
| --- | --- | --- |
| P1.1 | llm_probe.sh exits 0 against all 3 LLM backends | Captured stdout with per-backend latency |
| P1.2 | specify helix-nano-bridge --help prints usage for all 5 commands | Captured terminal output |
| P1.3 | MCP server connects to Claude Code — superbridge-mcp listed in ListTools | MCP handshake log |
| P1.4 | CM-HELIX-NANO-BRIDGE-EXTENSION-EXISTS gate GREEN | pre_build_verification.sh log |
| P1.5 | Paired §1.1 mutation FAILs the gate | meta_test_false_positive_proof.sh log |

### Phase 2 Success Criteria

| # | Criterion | Evidence Type |
| --- | --- | --- |
| P2.1 | decompose produces valid nano-tasks.json from 10 diverse tasks.md files | 10 nano-tasks.json files, all passing ajv validation |
| P2.2 | Dependency graph is acyclic for all 10 samples | Cycle detection: 0 cycles found |
| P2.3 | execute runs a full TDD cycle: RED fails → GREEN passes → VERIFY confirms | verdict.json with PASS and 3 iterations |
| P2.4 | Anti-bluff oracle: golden-good → PASS, golden-bad → FAIL | Oracle test log |
| P2.5 | All unit tests GREEN for library functions | Test runner output, 0 failures |

### Phase 3 Success Criteria

| # | Criterion | Evidence Type |
| --- | --- | --- |
| P3.1 | Full E2E: tasks.md (3 tasks) → decompose → execute → all GREEN | qa-results/e2e/full_pipeline.log |
| P3.2 | implementation-gate.js BLOCKS execution when RED test is missing | Gate exit 2, FAIL verdict |
| P3.3 | Retry recovers intentionally-failed tasks | Retry log: RED→GREEN→VERIFY for each recovered task |
| P3.4 | SuperB superb:ship blocked when nano-tasks not all GREEN | Ship gate log |
| P3.5 | User guide complete: HTML+PDF+DOCX exports pass CM-DOCS-EXPORT-SYNC | Export freshness gate GREEN |

### Phase 4 Success Criteria

| # | Criterion | Evidence Type |
| --- | --- | --- |
| P4.1 | 4 worker nodes execute 200 nano-tasks in parallel, throughput ≥ 10 tasks/s | Benchmark report in qa-results/benchmarks/ |
| P4.2 | Test coverage ≥ 85% line, ≥ 80% branch | Istanbul/NYC coverage report |
| P4.3 | Chaos tests: process death, disk full, OOM → graceful degradation (no crash) | Chaos test logs with recovery traces |
| P4.4 | Security audit: 0 HIGH, 0 MEDIUM findings | docs/audit/helix_nano_bridge_security.md |
| P4.5 | pre_build_verification.sh exit 0, 0 FAIL, 0 WARN on release tag | Full pre-build sweep log |
| P4.6 | Release tag helix-nano-bridge-v1.0.0 pushed to all remotes per §11.4.113 | git ls-remote --tags shows tag on all remotes |
| P4.7 | pack.sh archive SHA256 published and verified | Release manifest release-1.0.0.json |